# Mass Communications Equipment App Estimate

This estimate is for a custom-built, professional-grade web application developed by a freelance developer or a small development agency in the Midwest.

# Executive Summary

- Estimated Hours: 270 - 460 hours

- Estimated Cost: $25,000 - $60,000

- Estimated Timeline: 8 - 14 weeks (2 to 4 months)

The wide range in this estimate is almost entirely due to one critical factor: the difficulty of integrating with SIUE's IT systems. The answers from the IT department regarding student login (SSO) and access to course data will be the single biggest factor determining the final cost and timeline.

# Detailed Breakdown of Estimated Hours

Here is a phase-by-phase breakdown of the work involved.

| Phase / Feature | Estimated Hours | Tasks Included |
| --- | --- | --- |
| 1. Design & Prototyping | 20 - 40 hours | Creating a high-fidelity, clickable design based on the existing wireframes; establishing the visual style (colors, fonts); ensuring the layout is responsive for desktop and mobile. |
| 2. Frontend Development (Student View) | 80 - 120 hours | Building the user-facing part of the app: Login screen, dashboard, equipment catalog with search/filters, the reservation calendar/block selection interface, user account page, and QR code generation. |
| 3. Backend Development (Admin & Logic) | 100 - 160 hours | Building the "engine" of the app: Setting up the database, writing the core business logic (block limits, user permissions), and building the complete admin panel for staff to manage equipment, users, fees, and overrides. |
| 4. IT Systems Integration | 30 - 80 hours | This is the most variable component. It includes connecting to SIUE's SSO for login and, most importantly, building the system to sync with university course data (e.g., via an API or data feed from Banner) to automate user permissions. |
| 5. Testing & Deployment | 40 - 60 hours | Thoroughly testing every feature to find and fix bugs, setting up the live server environment, deploying the application, and final training/hand-off. |
| TOTAL | 270 - 460 hours |  |

# Explanation of Cost & Variables

## 1. The IT Integration Wildcard

This is the most significant variable.

- Best-Case Scenario (Lower end of the estimate): SIUE's IT department has a modern, well-documented API. Connecting to it is straightforward for an experienced developer.

- Worst-Case Scenario (Higher end of the estimate): The university systems are older, have no API, and require a complex or manual workaround (like staff uploading a spreadsheet of eligible students each semester). This adds significant complexity and development time.

## 2. Developer's Hourly Rate

The total dollar cost depends on who builds the app. Rates can vary widely:

- Freelance Developer (Midwest): $75 - $125 per hour

- Small Development Agency: $125 - $175+ per hour

My cost estimate of $25,000 - $60,000 uses a blended range to account for these rates and the integration variables mentioned above.

## 3. Ongoing Costs

Remember to budget for ongoing operational costs after the initial build, which are typically minor:

- Hosting: ~$20 - $50 per month for a reliable web server.

- Maintenance & Support: A yearly retainer or as-needed hourly work for updates, bug fixes, and security patches.

This estimate provides a realistic financial and time-based framework for your project. The very next step is to get firm answers from the IT department, which will allow you to narrow down this estimate to a much more precise figure.